## FINAL as of June 13 2014
EXHIBIT A
AMENDMENT # 1 to ENA for 12th Street Remainder Parcel
Revised Schedule of Performance, ending January 2, 2015
|  |  |  | Property: | 12th Street Remainder Parcel at E12th St & 2nd Ave
|  |  |  | Developer: | UrbanCore-Integral, LLC
|  | COMPLETED by July 2, 2014 |  | City Council Approval: | 2013-07-02 | Reso 84492 C.M.S.
|  | SUBMTTING by July 2, 2014 |  | Negotiation Period: | 12 months w +180 day extension option
|  | EXTENDED |  | Execution of ENA: | 2013-07-02
|  |  |  | Original End of Negotiation Period: | 2014-07-02
|  |  |  | End of Negotiation Period with +180 day extension: | 2015-01-02
|  | ENA Section # |  |  | # of Days from July 2, 2013 | Original Due Date | Notes
| 1 | 2.5.a | CEQA & PERMITS | City provides all existing enviromental, geological, engineering and other reports about Property's condition | 30 | 2013-08-01
| 2 | 2.5.b | DESIGN | Developer retains design team to prepare concept plans | 30 | 2013-08-01
| 3 | 2.2.a | MARKET STUDY | Complete market feasibility study | 60 | 2013-08-31
| 4 | 2.3.a | DESIGN | First public meeting on proposed development plan | 60 | 2013-08-31
| 5 | 2.1.a | PROJECT TEAM | Description of financial and legal structure of the Development Team, including partnership agreements, joint venture agreements, etc. | 90 | 2013-09-30
| 6 | 2.1.b | PROJECT TEAM | Balance sheets and income/loss statements for last 2 years(2012, 2013) for Development Team; including Developer's expanded team | 90 | 2013-09-30
| 7 | 2.1.c | PROJECT TEAM | Developer's LLC status | 90 | 2013-09-30
| 8 | 2.1.d | PROJECT TEAM | Development team's experience including: architect, structural engineers, general contractors, marketing & real estate firm | 90 | 2013-09-30
| 9 | 2.1.e | PROJECT TEAM | Development team's litigation status | 90 | 2013-09-30
| 10 | 2.5.b | CEQA & PERMITS | Developer retains enviromental consultants to prepare documents for CEQA review of Project. Developer's CEQA consultant shall compare proposed development project with the development program assumed for the Lake Merrit Station Area Plan. | 90 | 2013-09-30
| 11 | 2.3.a | DESIGN | Second public meeting on proposed development plan | 120 | 2013-10-30
| 12 | 2.5.c | CEQA & PERMITS | Submit Project Description for environmental review purposes to City | 120 | 2013-10-30
| 13 | 2.4.a.i | FINANCING | Conceptual Proformas: budget, sources & uses of funds, 10-yr cash flow, operating budget | 150 | 2013-11-29
| 14 | 2.4.a.ii | FINANCING | Project development schedule | 150 | 2013-11-29 |  | NEW # of Days From July 2, 2013 | NEW Due Date with Extension | # of Days Extended
| 15 | 2.4.a.iii | FINANCING | List of lenders and investors approached | 150 | 2013-11-29 |  | 363 | 2014-06-30 | 213
| 16 | 2.5.d | CEQA & PERMITS | Submit applicable zoning and land use permit pre-applications and a schedule of approvals. | 150 | 2013-11-29 | Developer to provide updated project description for Planning application
| 17 | 2.5.d | CEQA & PERMITS | Developer’s CEQA consultant shall review the Lake Merritt Station Area Plan Environmental Impact Report (DEIR) to determine if it is adequate for CEQA clearance of the proposed development project, any additional work that may be required, and if there is anything unique about the project and/or its location. Developer shall meet with the City to discuss the proposed CEQA approach. | 150 | 2013-11-29
| 18 | 2.3.a | DESIGN | Third public meeting on proposed development plan | 150 | 2013-11-29 | Developer shall hold additional community meetings as reasonably required | 425 | 2014-08-31 | 275
| 19 | 2.5.e | CEQA & PERMITS | Based on the specific CEQA approach for the project, Developer’s CEQA consultant shall prepare a draft scope of work, based upon the City’s “Guidelines for Environmental Consultant Contracts Concerning Private Development Projects” (dated 1/5/12), for City review and approval, that analyzes the specific environmental topics and type of CEQA document that is required to complete CEQA clearance – Initial Study, Addendum and/or Supplemental EIR. | 180 | 2013-12-29 | City gave LSA Notice to Proceed in May 2014. CEQA work underway
| 20 | 2.3.b | DESIGN | Schematic Design Plans, plan for public art, and list of public improvements, including adjacent park | 240 | 2014-02-27 | Conceptual designs submitted but more detailed schematic designs will be needed for selected project description and program | 374-394 | 31-Jul-14 | 135-154
| 21 | 2.5.d | CEQA & PERMITS | Submit applicable zoning and land use permit applications and a schedule of approvals. | 240 | 2014-02-27 | Developer to provide updated project description and final Schematic Plans for Planning application | 394 | 2014-07-31 | 154
| 22 | 2.5.f | CEQA & PERMITS | If supplemental/subsequent EIR is required, Developer's CEQA consultant shall cause the issuance of a NOP subject to City review and approval | 240 | 2014-02-27 | N/A - a supplemental/ subsequent EIR not required
| 23 | 2.4.b | FINANCING | UPDATED & REFINED: Project development schedule | 240 | 2014-02-27 | For the selected project design and program | 455 | 2014-09-30 | 215
| 24 | 2.5.g | CEQA & PERMITS | If Addendum and/or other non-EIR CEQA document is required, submit an adminstrative draft of the CEDA document | 270 | 2014-03-29 | Need to confirm with LSA | 455 | 2014-09-30 | 185
| 25 | 2.2.b | MARKET STUDY | Complete marketing strategy | 270 | 2014-03-29 |  | 435 | 2014-09-10 | 165
| 26 | 2.4.c | FINANCING | UPDATED & REFINED: Proformas: budget, sources & uses of funds, 10-yr cash flow, operating budget | 270 | 2014-03-29 | For the selected project design and program | 455 | 2014-09-30 | 185
| 27 | 2.4.d | FINANCING | LOI from lenders and equity partners to finance project | 300 | 2014-04-28 |  | 525 | 2014-12-09 | 225
| 28 | 2.6.a | DDA | City submits final appraisal report | 300 | 2014-04-28 |  | 485 | 2014-10-30 | 185
| 29 | 2.6.b | DDA | Complete DDA Negotiations | 330 | 2014-05-28 | Expected DDA period will be between January 2015 and January 2016 with land transfer by June 2015 | 520 | 2014-12-04 | 190
| 30 | 2.5.h | CEQA & PERMITS | Complete CEQA review. Developer: Complete enviromental assessment, ID site mitigations. City: complete enviro review, file Notice of Determination. | 330 | 2014-05-28 |  | 500 | 2014-11-14 | 170
| 31 | 2.5.h | CEQA & PERMITS | Obtain all zoning permits and necessary planning approvals, per the Planning Department and other advisory bodies, as needed, such as Parks and Recreation Advisory Committee (PRAC) | 360 | 2014-06-27 |  | 535 | 2014-12-19 | 175

## UCI RESPONSE June 2014
EXHIBIT A
AMENDMENT # 1 to ENA for 12th Street Remainder Parcel
Revised Schedule of Performance, ending January 2, 2015
|  |  |  | Property: | 12th Street Remainder Parcel at E12th St & 2nd Ave
|  |  |  | Developer: | UrbanCore-Integral, LLC
|  | COMPLETE |  | City Council Approval: | 2013-07-02
|  | SUBMTTING |  | Negotiation Period: | 12 months w 180 day extension option
|  | EXTENDED TERM |  | Execution of ENA: | 2013-07-02
|  |  |  | Original End of Negotiation Period: | 2014-07-02
|  |  |  | End of Negotiation Period with +180 day extension: | 2015-01-02
|  | ENA Section # |  |  | Within # of calendar days of the commencement of the negotiation period | Approx due date assuming July 2 execution | Notes
| 1 | 2.5.a | CEQA & PERMITS | City provides all existing enviromental, geological, engineering and other reports about Property's condition | 30 | 2013-08-01
| 2 | 2.5.b | DESIGN | Developer retains design team to prepare concept plans | 30 | 2013-08-01
| 3 | 2.2.a | MARKET STUDY | Complete market feasibility study | 60 | 2013-08-31
| 4 | 2.3.a | DESIGN | First public meeting on proposed development plan | 60 | 2013-08-31
| 5 | 2.1.a | PROJECT TEAM | Description of financial and legal structure of the Development Team, including partnership agreements, joint venture agreements, etc. | 90 | 2013-09-30
| 6 | 2.1.b | PROJECT TEAM | Balance sheets and income/loss statements for last 2 years(2012, 2013) for Development Team; including Developer's expanded team | 90 | 2013-09-30
| 7 | 2.1.c | PROJECT TEAM | Developer's LLC status | 90 | 2013-09-30
| 8 | 2.1.d | PROJECT TEAM | Development team's experience including: architect, structural engineers, general contractors, marketing & real estate firm | 90 | 2013-09-30
| 9 | 2.1.e | PROJECT TEAM | Development team's litigation status | 90 | 2013-09-30
| 10 | 2.5.b | CEQA & PERMITS | Developer retains enviromental consultants to prepare documents for CEQA review of Project. Developer's CEQA consultant shall compare proposed development project with the development program assumed for the Lake Merrit Station Area Plan. | 90 | 2013-09-30
| 11 | 2.3.a | DESIGN | Second public meeting on proposed development plan | 120 | 2013-10-30
| 12 | 2.5.c | CEQA & PERMITS | Submit Project Description for environmental review purposes to City | 120 | 2013-10-30
| 13 | 2.4.a.i | FINANCING | Conceptual Proformas: budget, sources & uses of funds, 10-yr cash flow, operating budget | 150 | 2013-11-29
| 14 | 2.4.a.ii | FINANCING | Project development schedule | 150 | 2013-11-29 |  | Proposed extension (days from July 2, 2014) | Due date assuming proposed extension | # of days extended
| 15 | 2.4.a.iii | FINANCING | List of lenders and investors approached | 150 | 2013-11-29 |  | 363 | 2014-06-30 | 213
| 16 | 2.5.d | CEQA & PERMITS | Submit applicable zoning and land use permit pre-applications and a schedule of approvals. | 150 | 2013-11-29 | Developer to provide updated project description for Planning application
| 17 | 2.5.d | CEQA & PERMITS | Developer’s CEQA consultant shall review the Lake Merritt Station Area Plan Environmental Impact Report (DEIR) to determine if it is adequate for CEQA clearance of the proposed development project, any additional work that may be required, and if there is anything unique about the project and/or its location. Developer shall meet with the City to discuss the proposed CEQA approach. | 150 | 2013-11-29
| 18 | 2.3.a | DESIGN | Third public meeting on proposed development plan | 150 | 2013-11-29 | Developer shall hold additional community meetings as reasonably required | 425 | 2014-08-31 | 275
| 19 | 2.5.e | CEQA & PERMITS | Based on the specific CEQA approach for the project, Developer’s CEQA consultant shall prepare a draft scope of work, based upon the City’s “Guidelines for Environmental Consultant Contracts Concerning Private Development Projects” (dated 1/5/12), for City review and approval, that analyzes the specific environmental topics and type of CEQA document that is required to complete CEQA clearance – Initial Study, Addendum and/or Supplemental EIR. | 180 | 2013-12-29 | City gave LSA Notice to Proceed in May 2014. CEQA work underway
| 20 | 2.3.b | DESIGN | Schematic Design Plans, plan for public art, and list of public improvements, including adjacent park | 240 | 2014-02-27 | Conceptual designs submitted but more detailed schematic designs will be needed for selected project description and program | 378-392 | 31-Jul-14 | 139-154
| 21 | 2.5.d | CEQA & PERMITS | Submit applicable zoning and land use permit applications and a schedule of approvals. | 240 | 2014-02-27 | Developer to provide updated project description for Planning application | 394 | 2014-07-31 | 139-154
| 22 | 2.5.f | CEQA & PERMITS | If supplemental/subsequent EIR is required, Developer's CEQA consultant shall cause the issuance of a NOP subject to City review and approval | 240 | 2014-02-27 | N/A - a supplemental/ subsequent EIR not required
| 23 | 2.4.b | FINANCING | UPDATED & REFINED: Project development schedule | 240 | 2014-02-27 | For the selected project design and program | 455 | 2014-09-30 | 215
| 24 | 2.5.g | CEQA & PERMITS | If Addendum and/or other non-EIR CEQA document is required, submit an adminstrative draft of the CEDA document | 270 | 2014-03-29 | Need to confirm with LSA | 455 | 2014-09-30 | 185
| 25 | 2.2.b | MARKET STUDY | Complete marketing strategy | 270 | 2014-03-29 |  | 435 | 2014-09-10 | 165
| 26 | 2.4.c | FINANCING | UPDATED & REFINED: Proformas: budget, sources & uses of funds, 10-yr cash flow, operating budget | 270 | 2014-03-29 | For the selected project design and program | 455 | 2014-09-30 | 185
| 27 | 2.4.d | FINANCING | LOI from lenders and equity partners to finance project | 300 | 2014-04-28 |  | 525 | 2014-12-09 | 225
| 28 | 2.6.a | DDA | City submits final appraisal report | 300 | 2014-04-28 |  | 485 | 2014-10-30 | 185
| 29 | 2.6.b | DDA | Complete DDA Negotiations | 330 | 2014-05-28 | Expected DDA period will be between January 2015 and January 2015 with land sale in June 2015 | 520 | 2014-12-04 | 190
| 30 | 2.5.h | CEQA & PERMITS | Complete CEQA review. Developer: Complete enviromental assessment, ID site mitigations. City: complete enviro review, file Notice of Determination. | 330 | 2014-05-28 |  | 500 | 2014-11-14 | 170
| 31 | 2.5.h | CEQA & PERMITS | Obtain all zoning permits and necessary planning approvals, per the Planning Department and other advisory bodies, as needed, such as Parks and Recreation Advisory Committee (PRAC) | 360 | 2014-06-27 |  | 535 | 2014-12-19 | 175

## CITY RESPONSE June 2014
EXHIBIT A
AMENDMENT # 1 to ENA for 12th Street Remainder Parcel
Revised Schedule of Performance, ending January 2, 2015
|  |  |  | Property: | 12th Street Remainder Parcel at E12th St & 2nd Ave
|  |  |  | Developer: | UrbanCore-Integral, LLC
|  | COMPLETE |  | City Council Approval: | 2013-07-02
|  | SUBMTTING |  | Negotiation Period: | 12 months w 180 day extension option
|  | EXTENDED TERM |  | Execution of ENA: | 2013-07-02
|  |  |  | Original End of Negotiation Period: | 2014-07-02
|  |  |  | End of Negotiation Period with +180 day extension: | 2015-01-02
|  | ENA Section # |  |  | Within # of calendar days of the commencement of the negotiation period | Approx due date assuming July 2 execution | Notes
| 1 | 2.5.a | CEQA & PERMITS | City provides all existing enviromental, geological, engineering and other reports about Property's condition | 30 | 2013-08-01
| 2 | 2.5.b | DESIGN | Developer retains design team to prepare concept plans | 30 | 2013-08-01
| 3 | 2.2.a | MARKET STUDY | Complete market feasibility study | 60 | 2013-08-31
| 4 | 2.3.a | DESIGN | First public meeting on proposed development plan | 60 | 2013-08-31
| 5 | 2.1.a | PROJECT TEAM | Description of financial and legal structure of the Development Team, including partnership agreements, joint venture agreements, etc. | 90 | 2013-09-30
| 6 | 2.1.b | PROJECT TEAM | Balance sheets and income/loss statements for last 2 years(2012, 2013) for Development Team; including Developer's expanded team | 90 | 2013-09-30
| 7 | 2.1.c | PROJECT TEAM | Developer's LLC status | 90 | 2013-09-30
| 8 | 2.1.d | PROJECT TEAM | Development team's experience including: architect, structural engineers, general contractors, marketing & real estate firm | 90 | 2013-09-30
| 9 | 2.1.e | PROJECT TEAM | Development team's litigation status | 90 | 2013-09-30
| 10 | 2.5.b | CEQA & PERMITS | Developer retains enviromental consultants to prepare documents for CEQA review of Project. Developer's CEQA consultant shall compare proposed development project with the development program assumed for the Lake Merrit Station Area Plan. | 90 | 2013-09-30
| 11 | 2.3.a | DESIGN | Second public meeting on proposed development plan | 120 | 2013-10-30
| 12 | 2.5.c | CEQA & PERMITS | Submit Project Description for environmental review purposes to City | 120 | 2013-10-30
| 13 | 2.4.a.i | FINANCING | Conceptual Proformas: budget, sources & uses of funds, 10-yr cash flow, operating budget | 150 | 2013-11-29
| 14 | 2.4.a.ii | FINANCING | Project development schedule | 150 | 2013-11-29 |  | Extension (days rom July 2, 2014) | Extended Due Date | # of days extended
| 15 | 2.4.a.iii | FINANCING | List of lenders and investors approached | 150 | 2013-11-29 |  | 363 | 2014-06-30 | 213
| 16 | 2.5.d | CEQA & PERMITS | Submit applicable zoning and land use permit pre-applications and a schedule of approvals. | 150 | 2013-11-29 | Developer to provide updated project description for Planning application
| 17 | 2.5.d | CEQA & PERMITS | Developer’s CEQA consultant shall review the Lake Merritt Station Area Plan Environmental Impact Report (DEIR) to determine if it is adequate for CEQA clearance of the proposed development project, any additional work that may be required, and if there is anything unique about the project and/or its location. Developer shall meet with the City to discuss the proposed CEQA approach. | 150 | 2013-11-29
| 18 | 2.3.a | DESIGN | Third public meeting on proposed development plan | 150 | 2013-11-29 | Developer shall hold additional community meetings as reasonably required | 425 | 2014-08-31 | 275
| 19 | 2.5.e | CEQA & PERMITS | Based on the specific CEQA approach for the project, Developer’s CEQA consultant shall prepare a draft scope of work, based upon the City’s “Guidelines for Environmental Consultant Contracts Concerning Private Development Projects” (dated 1/5/12), for City review and approval, that analyzes the specific environmental topics and type of CEQA document that is required to complete CEQA clearance – Initial Study, Addendum and/or Supplemental EIR. | 180 | 2013-12-29 | City gave LSA Notice to Proceed in May 2014. CEQA work underway
| 20 | 2.3.b | DESIGN | Schematic Design Plans, plan for public art, and list of public improvements, including adjacent park | 240 | 2014-02-27 | Conceptual designs submitted but more detailed schematic designs will be needed for selected project description and program | 363 | 2014-06-30 | 123
| 21 | 2.5.d | CEQA & PERMITS | Submit applicable zoning and land use permit applications and a schedule of approvals. | 240 | 2014-02-27 | Developer to provide updated project description for Planning application | 394 | 2014-07-31 | 154
| 22 | 2.5.f | CEQA & PERMITS | If supplemental/subsequent EIR is required, Developer's CEQA consultant shall cause the issuance of a NOP subject to City review and approval | 240 | 2014-02-27 | N/A - a supplemental/ subsequent EIR not required
| 23 | 2.4.b | FINANCING | UPDATED & REFINED: Project development schedule | 240 | 2014-02-27 | For the selected project design and program | 455 | 2014-09-30 | 215
| 24 | 2.5.g | CEQA & PERMITS | If Addendum and/or other non-EIR CEQA document is required, submit an adminstrative draft of the CEDA document | 270 | 2014-03-29 | Need to confirm with LSA | 455 | 2014-09-30 | 185
| 25 | 2.2.b | MARKET STUDY | Complete marketing strategy | 270 | 2014-03-29 |  | 435 | 2014-09-10 | 165
| 26 | 2.4.c | FINANCING | UPDATED & REFINED: Proformas: budget, sources & uses of funds, 10-yr cash flow, operating budget | 270 | 2014-03-29 | For the selected project design and program | 455 | 2014-09-30 | 185
| 27 | 2.4.d | FINANCING | LOI from lenders and equity partners to finance project | 300 | 2014-04-28 |  | 525 | 2014-12-09 | 225
| 28 | 2.6.a | DDA | City submits final appraisal report | 300 | 2014-04-28 |  | 455 | 2014-09-30 | 155
| 29 | 2.6.b | DDA | Complete DDA Negotiations | 330 | 2014-05-28 | Expected DDA period will be between January 2015 and January 2015 with land sale in June 2015 | 520 | 2014-12-04 | 190
| 30 | 2.5.h | CEQA & PERMITS | Complete CEQA review. Developer: Complete enviromental assessment, ID site mitigations. City: complete enviro review, file Notice of Determination. | 330 | 2014-05-28 |  | 500 | 2014-11-14 | 170
| 31 | 2.5.h | CEQA & PERMITS | Obtain all zoning permits and necessary planning approvals, per the Planning Department and other advisory bodies, as needed, such as Parks and Recreation Advisory Committee (PRAC) | 360 | 2014-06-27 |  | 535 | 2014-12-19 | 175

## UCI PROPOSED DATES April 2014
REVISED DECEMBER 2013: UPDATED WORKING SCHEDULE, ASSUMING LMSAP & EIR GETS ADOPTED JUNE 2014, AND PROJECT'S CEQA REVIEW BEGINS NOW, BASED ON LMSAP'S DRAFT EIR
EXCLUSIVE NEGOTIATING AGREEMENT - SCHEDULE OF PERFORMANCE
|  | Property: | 12th Street Remainder Parcel
|  | Approximate CED approval: | 2013-06-25
COMPLETE
| SUBMTTING | Approximate City Council Approval: | 2013-07-02
| EXTENDED TERM | Negotiation Period: | 12 months w 180 day extension option
|  | Approximate Execution of ENA: | 2013-07-02
|  |  | Within # of Calendar days of the Commencement of the Negotiation Period | Approx due date assuming July 2 execution | Actual Status as of 4/15/14 | REVISED DATES PROPOSED | Approx due date assuming July 2 execution | AMOUNT OF TIME EXTENDED
1 | CEQA & PERMITS | City provides all existing enviromental, geological, engineering and other reports about Property's condition | 30 | 2013-08-01 | complete
2 | DESIGN | Developer retains design team to prepare concept plans | 30 | 2013-08-01 | complete
3 | MARKET STUDY | Complete market feasibility study | 60 | 2013-08-31 | complete
4 | DESIGN | First public meeting on proposed development plan | 60 | 2013-08-31 | complete
5 | PROJECT TEAM | Description of financial and legal structure of the Development Team, including partnership agreements, joint venture agreements, etc. | 90 | 2013-09-30 | pls submit ASAP
6 | PROJECT TEAM | Balance sheets and income/loss statements for last 2 years(2011, 2012) for Development Team; including Developer's expanded team | 90 | 2013-09-30 | pls submit ASAP
7 | PROJECT TEAM | Developer's LLC status | 90 | 2013-09-30 | pls submit ASAP
8 | PROJECT TEAM | Development team's experience including: architect, structural engineers, general contractors, marketing & real estate firm | 90 | 2013-09-30 | pls submit ASAP
9 | PROJECT TEAM | Development team's litigation status | 90 | 2013-09-30 | pls submit ASAP
10 | CEQA & PERMITS | Developer retains enviromental consultants to prepare documents for CEQA review of Project. Developer's CEQA consultant shall compare proposed development project with the development program assumed for the Lake Merrit Station Area Plan. | 90 | 2013-09-30 | We should aim for your CEQA consultant to meet with the necessary City staff, including Planner Neil Gray, to discuss the proposed Scope/CEQA approach in January 2014
11 | DESIGN | Second public meeting on proposed development plan | 120 | 2013-10-30 | Complete; we can count your meeting with the Measure DD Coalition; pls keep me posted on any special meeting w 1200 Lakeshore - I'd like to be aware and attend, if possible
12 | CEQA & PERMITS | Submit Project Description for environmental review purposes to City | 120 | 2013-10-30 | pls submit ASAP, if not already done
13 | FINANCING | Proformas: budget, sources & uses of funds, 10-yr cash flow, operating budget | 150 | 2013-11-29 | pls submit ASAP
14 | FINANCING | Project development schedule | 150 | 2013-11-29 | pls submit ASAP
15 | FINANCING | List of lenders and investors approached | 150 | 2013-11-29 | pls submit ASAP | 330 | 2014-05-30 | +60 Days
16 | CEQA & PERMITS | Submit applicable zoning and land use permit pre-applications and a schedule of approvals. | 150 | 2013-11-29 | pls submit ASAP, if not already done
17 | CEQA & PERMITS | Developer’s CEQA consultant shall review the Lake Merritt Station Area Plan Environmental Impact Report (DEIR) to determine if it is adequate for CEQA clearance of the proposed development project, any additional work that may be required, and if there is anything unique about the project and/or its location. Developer shall meet with the City to discuss the proposed CEQA approach. | 150 | 2013-11-29 | We should aim for your CEQA consultant to meet with the necessary City staff, including Planner Neil Gray, to discuss the proposed Scope/CEQA approach in January 2014
18 | DESIGN | Third public meeting on proposed development plan | 150 | 2013-11-29 | To be determined; should happen before project's CEQA document goes to Planning Commission for approval. | 420 | 2014-08-31 | +270 Days
19 | CEQA & PERMITS | Based on the specific CEQA approach for the project, Developer’s CEQA consultant shall prepare a draft scope of work, based upon the City’s “Guidelines for Environmental Consultant Contracts Concerning Private Development Projects” (dated 1/5/12), for City review and approval, that analyzes the specific environmental topics and type of CEQA document that is required to complete CEQA clearance – Initial Study, Addendum and/or Supplemental EIR. | 180 | 2013-12-29 | We should aim for your CEQA consultant to meet with the necessary City staff, including Planner Neil Gray, to discuss the proposed Scope/CEQA approach in January 2014 | 300 | 2014-04-30 | +120 Days
20 | DESIGN | Schematic Design Plans, plan for public art, and list of public improvements, including adjacent park | 240 | 2014-02-27 | We will need to discuss/get more clear on the process for submitting your design proposal for the park for City's consideration | 390 | 2014-07-31 | +150 Days
| CEQA & PERMITS | Submit applicable zoning and land use permit applications and a schedule of approvals. | 240 | 2014-02-27 |  | 390 | 2014-07-31 | +150 Days
21 | CEQA & PERMITS | If supplemental/subsequent EIR is required, Developer's CEQA consultant shall cause the issuance of a NOP subject to City review and approval | 240 | 2014-02-27 |  | 300 | 2014-04-30 | +60 Days
22 | FINANCING | UPDATED & REFINED: Project development schedule | 240 | 2014-02-27 |  | 300 | 2014-04-30 | +60 Days
23 | CEQA & PERMITS | If Addendum and/or other non-EIR CEQA document is required, submit an adminstrative draft of the CEDA document | 270 | 2014-03-29 |  | 450 | 2014-09-30 | +180 Days
24 | MARKET STUDY | Complete marketing strategy | 270 | 2014-03-29 |  | 390 | 2014-07-31 | +180 Days
25 | FINANCING | UPDATED & REFINED: Proformas: budget, sources & uses of funds, 10-yr cash flow, operating budget | 270 | 2014-03-29 |  | 420 | 2014-08-31 | +180 Days
26 | FINANCING | LOI from lenders and equity partners to finance project | 300 | 2014-04-28 |  | 450 | 2014-09-30 | +150 Days
27 | DDA | City submits final appraisal report | 300 | 2014-04-28 |  | 450 | 2014-09-30 | +150 Days
28 | DDA | Complete DDA Negotiations | 330 | 2014-05-28 |  | 540 | 2015-01-02 | +210 Days
29 | CEQA & PERMITS | Complete CEQA review. Developer: Complete enviromental assessment, ID site mitigations. City: complete enviro review, file Notice of Determination. | 330 | 2014-05-28 | Assuming LMSAP & EIR gets approved by Planning Commission and then City Council in June 2014, the earliest your project's CEQA document can be scheduled for Planning Commission hearing is July 2014. | 480 | 2014-10-31 | +150 Days
30 | CEQA & PERMITS | Obtain all zoning permits and necessary planning approvals, per the Planning Department and other advisory bodies, as needed, such as Parks and Recreation Advisory Committee (PRAC) | 360 | 2014-06-27 | Following any other required advisory body approval hearings, the earliest this project's CEQA and DDA will get scheduled for City Council approval is probably September 2014. (Before July 2, we will need to formally amend our ENA to allow for time extension). | 510 | 2014-11-30 | +150 Days
|  | COMPLETE ENA | 360 |  |  | 540 | 2015-01-02 | +180 Days

## Sheet2
Planning Commission
Schematic Designs
Community Meetings
CEQA Document - Admin Draft
PRAC
CEQA Document - Final Draft
Planning Commission
City Council